## Sheet1
Northville City Council 2023-2025 Strategic Priorities Approved: June 2023 Updated: September 2023; December 2023; March 2024: June 2024; September 2024
I. | High Performing Government: Good Governance
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Fiscally responsible and accountable organization | 1. | Ensure financial solvency | a. | Increase OPEB and pension funding percentages | Finance | Per the December 2022 valuations, the pension plan is 92% funded and OPEB is 115% funded. The City contributed an additional $1.29 million towards the pension plan in calendar year 2023. A new valuation is expected in June 2024. A new valuation for the OPEB plan is expected first quarter 2024. The OPEB valuation for December 2023 has been received. The plan is 158% funded. There are currently 68 participants and 9 actives in the plan. The December 2023 pension valuation has been received. The plan is 104% funded. The plan needs approximately $3.3 million to achieve 120% funded status. No change for September 2024. Pension is 104% funded and OPEB is 158% funded.
|  |  |  | b. | Conduct direct-indirect cost allocation study | Finance | City Council approved Municipal Analytics to perform this work on 9/7/23. Kickoff meeting was 9/14/23. The study is complete and staff is reviewing. It will be incorporated into the FY25 budget. COMPLETED
|  |  |  | c. | Increase bond rating from AA+ to AAA | Finance | Focusing on building and maintaining fund balance. Per the FY23 Audit Report, General Fund fund balance was at 29.9%. The goal for potential bond rating increase is 30% or higher. The proposed FY25 budget has been established with projected fund balance in the General Fund at 31%. Nothing new to report this quarter. The City currently does not have a bond rating since general obligation bonds have not been issued recently. GO bonds will likely be issued this fiscal year for water improvements and the City will go through a rating review process this spring.
|  | 2 | Pursue exterior funding sources and administer program requirements | a. | Complete an inventory of outstanding grants and develop grant implementation timelines | CM/SP | A spreadsheet has been developed of all grants and pertinent information grant information. This will continue to be updated regularly. The spreadsheet continues to be updated regularly. Current grant funded projects are underway, and a program and timeline for pursuing additional grant funds is being developed. Project budgets have been developed for each grant and capital improvement project. The project budgets include revenue and expenses for each project beginning this fiscal year through 2026. The grant inventory continues to be updated, a copy of which is attached. The city has received more that $8.5 million in grant funds since 2022. Currently there are funding requests pending in excess of $2 million. The spreadsheet and project budgets continue to be updated and monitored.
|  |  |  | b. | Develop a grant policy | CM/Fin. | No update. A policy has been drafted. A draft policy will be reviewed by staff with a goal to finalize by June 30, 2024. The draft policy is currently being reviewed by the City Manager's office. COMPLETED with an effective date of August 21, 2024, and distributed among staff.
|  |  |  | c. | Explore funding opportunities to implement the Ford Field Master Plan and downtown dev. plan, including grants, donations, and public/private partnerships. | CM/SP | A Revitalization and Placemaking grant was submitted to reconstruct Ford Field Playground. The RAP 2.0 grant request to replace Ft. Griswold was unsuccessful and alternative funding options are under consideration. A preliminary design plan is being developed to help in pursuing alternative funding opportunities, including private fundraising. Funding options for the restrooms and Ford Field Park East will be incorporated into the grant program outlined in Action a, of Strategy 2 above. A Land and Water Conservation Fund grant application has been submitted for funds to construct a restroom and accessible walkways, and a Public Places/Community Spaces grant is being pursued for the playground replacement. See Item VI.A. for updates The preliminary scoring of the Land and Water Conservation Fund grant application was received and additional information was submitted to improve the likelihood of project funding. Final grant scores and a decision on funding will be available in November.
|  | 3. | Ensure services are provided in the most efficient and cost effective manner. | a. | Evaluate staffing levels and needs to ensure right-level staffing, including cost effectively using of consultants | CM | Added Director of Strategic Planning and Special Projects to manage grants and projects in house. Evaluating current staffing levels/expertise, and where additional support is likely to be needed due to the Downs and Foundry Flask projects. A recommendation is being prepared for the Personnel Committee related to community development and planning. Actively recruiting a community development director. FT Community Development Director started in June. The city's communication and marketing needs are being evaluated with the intent of pursing contract services for this item.
|  | 4. | Provide for stable revenue streams | a. | Reduce turn-around time on apartments in Allen Terrace | AT | Prep time has been cut in half. What was taking 6-8 weeks, took 3 weeks with the last vacancy. Turn-around is still taking 3-4 weeks which is a bit longer than last quarter because new flooring is being installed in each unit at turn-over. This is still 2 weeks less than the historic schedule. Apartment prep is down to 2-3 weeks. No changes to report. We continue to focus on efficient turn-arounds. Two new residents moved in this quarter and there are 135 persons on the waiting list.
B. | Responsive and accessible service | 1. | Provide a variety of ways to inform citizens of important City Information | a. | Increase email newsletter subscriptions | CM/Comm | A City postcard to encourage enrollment in City News, Nixle and social media. The card is being distributed at all public events. City News enrollment is up slightly from 6/19/23 (@2,295) and the average open rate is 67% ( industry average is 45%). City News subscribers now at 2,321. Open rate ranges from 61 to 71% (industry average is 43% as of 12/27/23) Nixle: 2,919 total subscribers as of 12/27/23 (previous count was 2,886 - undated) - increase of 33 subscribers. Sent 120 messages via Nixle in 2023: relating to weather, water, air quality and 911 service. City News subscribers: 2,351 (+ 30). Nixle subscribers: 2,993, (+ 74). City News: 2,562 (+211); In April, started an email called Downs Redevelopment Update, geared to nearby residents and business owners who want more detailed information than what appears in City News, 517 subscribers. Open rate is 85%. Nixle: 3,045 (+52) City News subscribers: 2,574 (+12); Downs Redevelopment Update: 548 (+31), 84% open rate; Nixle subscribers: 3,101 (+56)
|  |  |  | b. | Increase followers of social media platforms and explore the enhanced use of Instagram and social media platforms | CM/Comm | Facebook: increased 164 followers in 3 months - now @ 2,564; X (formerly Twitter) 573 followers, increase of 18 in 3 months. FB: 2,700 followers - up 136 (5%) in 3 months; X: 590 followers; increase of 17 (3%) in 3 months FB: 2,800 followers - up 100 in 3 months; X: 648 followers; increase of 58 in 3 months. Explored the use of Instagram and determined it's not well suited to city business; the city is covered in this arena by DDA, which uses Instagram for events and retail/restaurant sector. FB followers: 2,800 (holding steady); X: 643 followers Facebook followers: 2,972 (+172); X: 681 (+38)
|  |  |  | c. | Evaluate option to film BZA, PC and HDC meetings | CM | No update. We are working with Diligent Communities to first start with City Council Agenda and Meeting Management to be implemented in 1st Quarter 2024. Once we progress through that we will assess the feasibility of including options for the three boards. This is on hold until the transition is made to Diligent Communities for meeting packets and meeting streaming and recording. Transition to Diligent is underway and this item remains on hold at this time There has been no change on this item as we continue to adjust to the Diligent platform.
|  |  |  | d. | Evaluate the use of Zoom for public meetings | CM | No update. We are working with Diligent Communities and MergeLive to continue these discussions on the most feasible options moving forward in 2024. City Council continues to offer meetings via Zoom but is not currently accepting public comment from online attendees. A number of options are being evaluated for streaming Council meetings online. Council meetings are now streamed live on YouTube with comments being accepted up until 4:00 pm for inclusion in the meeting packet. Zoom is no longer offered. No update this quarter
|  | 2. | Improve procedures for communicating with residents during emergency situations | a. | Promote and increase Nixle registration, and evaluate options to increase frequency of announcements | CM/Comm | 2,886 contacts - those registered learned of city-wide power outage, severe thunderstorms during a busy season of weather-related alerts. The City posted a total of 120 Nixle notices in 2023. Breakdown is as follows: > Weather related advisories, water main breaks and limit water usage: 1st Q - 15; 2nd Q - 18; 3rd Q - 43; 4th Q - 29 > Interruption of 911 services: once in August, once in Dec. > Air quality alerts: 2nd Q - 5; 3rd Q - 8 No Update 32 posts in 2nd quarter, compared to 18 posts in 2Q, 2023 - we are notifying the public more frequently with alerts and advisories 36 Nixel messages were issued in this quarter: 16 were announcements and alerts related to weather; and 20 were advisories related primarily to street closures and parades.
|  | 3. | Promote two-way communication with citizens | a. | Host open house meetings as appropriate. | CM | An open house was held for the 5-year Parks and Recreation Plan. A joint open house was held for the Non-Motorized Plan, Downtown Traffic Study, and the Ford Field Master Plan. A pre-construction meeting was held with Beal Town residents about the Yerkes water main and road project. An open house was held to gather community feedback on the Ford Field Master Plan and Gateway project. A public meeting was held to collect input on the Ford Field Accessible Gateway design options. A Downs Construction Information meeting was held on March 26 to share information with the community about the Downs project. The meeting was well attended with nearly 150 participants. A meeting was held with residents concerned about the dust being generated by the Downs project. City staff and engineers received feedback from the five residents present, who expressed appreciation for the opportunity. A community meeting was held to gather ideas for replacing the playground in Ford Field Park. Approximately 30 people attended and provided quality feedback. An on-line survey was also developed and posted. A public information meeting was held on August 12, to share information about the proposed roundabout at Center Street and 7-mile. It was an open house format and was well attended.
|  | 4. | Increase opportunities for face-to-face communication with residents | a. | Implement Coffee-with-Council. | CM | City Council has hosted four (4) Coffee with Council events. This program is proposed to restart in February, 2024. Coffee-with-Council was hosted February 15 and March 16, with consistent turnout. City Council housed three Coffee-with-Council events, one each on March 16, April 18 and May 18. After a summer break in July and August, Coffee-with-Council began again on September 19 and will continue into fall.
|  |  |  | b. | City Manager meet with neighborhoods and attend community interest meetings. | CM | City Manager attended three (3) neighborhood and/or association meetings. City Manager attended an assortment of community interest meetings this quarter including meeting with the Chamber, Coffee with Council, parade participation, and joining staff and business owners to discuss the FOG ordinance. City Manager attended Downs community construction meeting, two Coffees-with-Council and DDA outdoor dining meetings with business owners. The City Manager attended Coffee with Council meetings as well as several community meetings including Rotary, NCBA, Seniors Luncheon and Playground Committee. The City Manager attended Coffee with Council, the Senior Luncheon, and Chamber Business meeting.
II. | Vibrant Economy and Development
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Balanced parking system | 1. | Provide adequate parking to support visitor, business and resident needs | a. | Conduct a parking study including: facility & spaces inventory; compare rev-exp; maint. & capital program; long-term funding options | DPW | No Update. Staff to prepare RFP for parking study to evaluate existing parking requirements and capacity, operational costs, parking inventory, funding options and ability to meet zoning requirements. A Request for Proposals for a Parking Consultant is being prepared and is expected to be posted in April 2024 A Consultant Services Contract was awarded to Fishbeck on June 3, to conduct a Parking Management Study. Fishbeck has completed the parking inventory and conducted useage counts. A workshop with direct stakeholders in the downtown is being planned.
|  |  |  | b. | Develop plan to address parking enforcement | DDA/DPW/Police | The Police Department conducted a demo with a parking enforcement device company. Proposals were received from three suppliers of hand-held parking devices and staff are developing an evaluation system for the companies. We hope to conduct additional demos and pick a vendor in early 2024. Staff have conducted demos on several vendors and will recommend a preferred vendor to City Council in April/May. The program should be in place by early summer. City Council approved a parking enforcement vendor (Ballparc). The onboarding process has been started. We hope to have the program up and operational in July of 2024. BallPark system is operational and being used by officers. Currently using system for overnight parking and other parking enforcement. Broad timed parking enforcement will begin in the near future. Overall implementation of project put on hold until Parking Study is completed.
B. | Resilient and vibrant downtown | 1. | Provide a range of programs to support seasonal operation of the downtown | a. | Evaluate the existing menu of programs and offerings to ensure activation of the downtown during all seasons | DDA | The DDA currently offers activities in all seasons including summer concerts, Skeletons are Alive, A Holiday to Remember, Chili-n in the Ville. DDA staff is working through the Marketing Committee to identify existing and new events that are provided by the DDA and others in an effort to activate the downtown. DDA is in the process of reviewing the summer concert offerings to determine the most successful format for providing music in the downtown. DDA/PD/Clerk are working together to address music volume and scheduling and require Entertainment license as per MLCC requirements. The DDA has met with several event organizers to encourage programming of events by outside organizations with assistance by City and DDA staff including a summer car show. The DDA held a merchant meeting to discuss the use of chalk in the downtown and to explore additional ways to activate the areas within the street closures to provide more interest and activities for users. The DDA has begun planning for a combined concert/events calendar with the Chamber.
|  |  |  | b. | Develop strategic partnerships to expand program offerings in the downtown | DDA | DDA is working with several organizations to bring additional activities to the downtown, including a Cornhole Tournament. DDA staff is currently working with two private groups to bring new events to downtown and support existing downtown programming. DDA is working with the business owners to encourage additional planned music for the downtown provided by the private sector. DDA and P & R exploring additional collaborative programming. The City, DDA and Chamber continue to work together to provide concerts throughout the summer. In addition, the DDA is working with the NCBA to support events to drive business to the downtown restaurants and stores including Sidewalk Sales, Witches Night Out, Girls Night Out. The Economic Development Committee is developing a Parklet concept that could be implemented in the downtown and would provide public spaces that could offer additional program offerings.
|  |  |  | c. | Develop downtown health metrics | DDA | The Downtown Building Inventory is completed. DDA staff has scheduled training on January 23rd on how to utilize program by project vendor. DDA exploring the use of summer interns to verify data in new building inventory database. DDA and Clerk's office looking at ways to utilize data provided by the business registration applications. Continuing work to complete data collection for Building Inventory in cooperation with the City Clerk's office. Equipment purchased and project is moving forward.
|  | 2. | Ensure downtown infrastructure is attractive and safe for all visitors | a. | Complete the bollard project and install planters | DDA | The bollards have been purchased for Center and Main Street. Bids have been accepted and a Contract awarded for the installation, which is anticipated to be completed in October. Three of the four corners of downtown have had the bollards installed. One corner - E. Main and N. Center Street will be installed in early spring. The bollards have been utilized successfully during the holiday lighted parade. DDA staff is currently utilizing the DDA's triple planters to fill the gaps created by the bollard locations. New designs for planters will be taken up by the Design Committee in early January. Design Committee scheduled for January to review/select planters. Remaining bollards at Center and Main Streets (northbound Center) were installed on March 27th. The bollards should be operationally by April 1st and the streets reopened for vehicular traffic. April 29th, the seasonal road closures on E. Main and N. Center will be activated. COMPLETED
|  |  |  | b. | Study the opportunity for curbless streets in the central downtown including an evaluation of similar communities who have implemented this approach | DDA/DPW | A consultant services contract was awarded for concept design and an informational meeting was held with downtown merchants to review and discuss the concepts. GMA provided graphics for the DDA/City to utilize when holding discussions with committee members and the public. In early January the DDA and City will explore contracting with the new City Engineers to perform pre-engineering to evaluate the conditions for a curbless street. City staffed vetted proposals from OHM and Spicer Group and will make a recommendation to the DDA Board at its April meetings. The $42,000 cost will be shared evenly by the City and DDA. The project should kick off in May, 2024. A project kick-off meeting was held and OHM is gathering base information to begin concept design. A topographic survey of the downtown streets has been completed by OHM, and concept ideas and design options have been developed, including material suggestions and construction concepts. Staff provided feedback which will be incorporated into the concepts and an estimate of probable cost prepared. OHM is also researching potential funding options.
III. | Strong Neighborhoods: Strong, Safe, Diverse Communities
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Stable neighborhoods | 1. | Provide clear priorities for land use | a. | Complete revisions to Historic District Design Guidelines | Building | Progress continues. The Design Guidelines consultant, Kraemer Group, delivered draft Guidelines for review at the November 15, 2023 HDC Meeting. The Kraemer Group, the City's Planning Consultant and the HDC Board are continuing with the final stages of creating a draft and then the draft will be discussed at community engagement sessions with a proposed final adoption in Sept 2024 Preliminary guidelines have been reviewed by the HDC and are being revised. A draft is expected to be forwarded to City Council for public review in June. On June 19, 2024 the HDC held a community engagement meeting with Kraemer Design Group and provided the public additional time to comment on the last draft of the Guidelines. To complete the project before the September grant deadline, the HDC will approve the final draft at its July meeting, and the guidelines will be sent to City Council for review/approval in August. COMPLETED
|  |  |  | b. | Update Zoning Ordinance to align with new Master Plan | Building | The Planning Commission determined priorities for ordinance updates and will focus on reviewing them (including this) during their 2024 sessions. This project is on hold until the planning and zoning staffing transition is complete. This summer the Planning Commission intends to forward its recommendation on an amendment to the Tree Preservation Ordinance to City Council for review/approval. Additionally, the Green Ordinance Audit currently underway will likely lead to Zoning Ordinance amendments which will address sustainability goals of the Master Plan. In August 2024 the Planning Commission discussed several staff-proposed Zoning Ordinance amendments; a public hearing on these amendments will be scheduled this fall. In September 2024 the Planning Commission discussed recommendations of the Green Ordinance Audit, which include new landscape/plant material standards.
|  |  |  | c. | Design and implement a historic district/house signage program | Building | No update. No Update No update. No update.
|  | 2 | Ensure residents' safety and security | a. | Complete the fire optimization study and implement recommendations | Fire | Northville City Fire Department paperwork has been submitted to Center for Public Safety Management (CPSM), the City's consultant on the project. CPSM is working with Superior and Huron Valley Ambulance to obtain additional data. Report is expected to be done at the end of the year. The consultant continues to compile data and develop the report. The report was finalized and released on Feb. 27, 2024. It has been sent to Northville City Council and Plymouth City Commission for review. The department is in the process of creating a Deputy Chief position as a part of the recommendation for more administrative capacity. Pending Council approval, the ladder truck will be sold to Northville Township and made available to the city as needed through mutual aid, allowing the city of Northville to benefit from the closer proximity of the truck.
|  |  |  | b. | Update Engineering Design Standards | DPW | Draft standards have been developed and are undergoing administrative review. Draft standards were completed and were approved by City Council on December 18. COMPLETED
|  |  |  | c. | Implement lead service line program in accordance with EGLE requirements, including inventory of service lines. | DPW | Reviewing inventory, replacing lead service lines as-needed along with construction projects. Future planning needed. Have received additional information from EGLE and will be developing a revised plan to ensure the City fulfills the new requirements. City was notified in March 2024 awarded $600,000 grant with no local match to help perform service line verification to assist with future replacement plan. The lead service line inventory and management program has to be completed by September, 2026. A proposal has been requested from OHM to oversee the program. A project kick-off meeting has been held with OHM and OHM is reviewing internal service data and compiling bid documents for a contractor to perform field verifications. Additionally public educational material is being developed.
B | Sustained population | 1. | Support approved development projects | a. | Foundry Flask | Building | Site Design and possible revisions are being considered by the applicant. No Update In June the Developer met with staff to discuss modifications to the Brownfield Plan, 381 Work Plan, and EGLE grant to accommodate a change in use, and intends to seek City Council approval of a 10-year tax abatement. The Planning Commission will need to review/approve the site plan amendment. In August the Developer met with staff to discuss modifications to the Brownfield Plan, 381 Work Plan, and EGLE grant to accommodate a change in use. A two-year extension to the EGLE grant is being requested. The Developer also intends to pursue planned unit development (PUD) approval for the proposed project. This submission is expected in a few months.
|  |  |  | b. | 711 N. Center Street Condos | Building | Project has been approved by the Planning Commission, and has received engineering approval and a tree removal permit. The Planning Commission approved the Preliminary Site Plan, with conditions and comments to address at the Final Site Plan stage. Over several meetings, the Planning Commission reviewed the Final Site Plan with the applicant, and ultimately approved it, with conditions. This included additional information regarding the condominium documents. No Update No update. In July 2024 the Planning Commission re-approved the final site plan / final condominium plan for the project. In August 2024 the Board of Zoning Appeals (BZA) re-approved the previously granted variances for the development. The previous approvals expired in June 2024. The Developer intends to begin site work soon.
|  | 2. | Support developments that complement the City's Master Plan | a. | Downs development | CM/ Building | The Downs development agreement has been approved and final site plans submitted for review. The Planning Commission approved the final site plan at the November 21, 2023 meeting. Work on the Downs has begun with asbestos abatement and pest control in preparation for demolition. Bi-weekly meetings are being held with a staff team to coordinate the various aspects of the project, and a Downs community construction meeting was held with a high turnout. Progress continues on the project. A full-time Code and Building official has been hired to monitor the site and coordinate inspections, and contracts have been issued for plumbing, building, and electrical inspectors dedicated to the Downs project. A full-time site inspector from OHM has been contracted to monitor construction methods with a focus on dust control, and a variety of other OHM engineering technicians are overseeing soil erosion and sedimentation control measure, water/sewer/storm installation, and grading and site work. The rough grading of the river is complete and the general elevation and alignment are now clearly visible. The gravel road base and curb and gutters are installed for the extensions of both Beal Street and Hutton Street and paving is expected in early October. The import of soil is well underway for the central sections of the Downs development and will continue for another 4-6 weeks. Building plans are under review for the structures on the old Farmers Market site, the appartments at Cady and Center Street, and the condominiums Griswold Street. Permits will be issued once all approvals and payment have been received.
|  | 3. | Support a safe school district for both public and private schools in the City | a. | School resource officer (SRO) and other programs to enhance school safety, including training, education and equipment. | Police | The City is moving forward with hiring an SRO per the agreement with the school. The SRO is expected to be in place by the end of December. The SRO has been hired and is starting on January 3rd. SSA Patrick Lindberg has been working in Hillside, Cooke and Amerman since January 3rd. He has built positive relationships with students, staff and parents during this short time. Nothing but positive feedback has been received. SSA Lindberg complete National Association of School Resource Officers (NASRO) Training on June 21, 2024 SSA Lindberg assisted the administration with projects during the summer months. He returned to HIllside on September 3, 2024.
|  |  |  | b. | Conduct an inventory of school routes and develop a Safe Routes to School plan | Police | No update. Staff continues to evaluate options for safe pedestrian routes along Doheny Drive and is working with the Township to explore a pedestrian crossing over 7-mile. This is still ongoing. This is ongoing. This is still ongoing
IV. | High Quality Environment: Environmental Sustainability
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Reduced environmental footprint | 1. | Utilize green infrastructure to mitigate storm water in the City | a. | Complete greening of Mill Race Project in cooperation with Historical Society | DPW | A Subrecipient Agreement with the Northville Historical Society was developed and executed. Construction plans will be finalized over the winter. The Northville Historical Society continues to work with F&V to finalize the construction plans. Northville Historical Society has accepted bids on the work. All bids were above the estimated costs. NHS is working with the low bidder on value engineering to reduce the costs and allow the project to move forward. The bricks for the entry drive have been delivered to site. A Construction Contract was awarded to D2 Contracting for the project and work is expected to begin on July 15. The Greening Mill Race project is complete and a ribbon cutting was held on September 15. Fundraising continues for the project via a brick paver program and city staff will be providing the granting agency the documentation required to close out the grant.
|  |  |  | b. | Monitor permeable pavement project and evaluate options for continue use | DPW | The current permeable pavement on Wing Ct has operated and functioned with minimum maintenance for the past two years. DPW currently researching maintenance options for cleaning . Have researched options for cleaning the pavement as recommended and determined that the most cost effective method was to contract this service. Have identified a company to perform the work and will be pursuing that in the spring. Weather permitting, cleaning will be scheduled Spring 2024. Additional contractors have been identified to perform the cleaning and have been contacted to provide quotes for the work. The length of permeable pavement (on Wing Court) was cleaned on July 25.
|  | 2. | Implement energy conservation measures to reduce utility usage | a. | Convert interior lights to LED with motion sensors, as appropriate | DPW | The lower level office reconstruction in City Hall includes LED upgrades. Scheduled for Fall 2023. Full city hall inventory with phasing and budgeting needed. The new offices in the lower level have been equipped with dimmable LED lights and as ballasts need to be replaced they are converted to LED. Staff is developing recommendations for a more strategic replacement plan. Continue to evaluate alternate options for energy savings including calibration of the HVAC system. No additional lights have been upgraded this quarter. No additional lights have been upgraded this quarter. However, locking covers have been installed over all thermostats to stabilize heating/cooling levels throughout City Hall. We continue to convert existing lights to LED as needed.
|  |  |  | b. | Install low-flow faucets in public restrooms at City Hall, where appropriate | DPW | No Update. A drinking fountain with a bottle filling feature has been installed on the 1st floor and we will be installing a low-flow faucet in one of the public restrooms to study its effectiveness. New water meter has been installed at City Hall to better monitor water usage. No additional updates at this time. No additional updates.
B. | Environmental sustainability and resiliency | 1. | Provide for the conservation of natural resources through reduction and recycling | a. | Study and evaluate transitioning to online agenda and packet platform | CM | The administration met with two companies and reviewed the proposals. Currently, evaluating next steps to work with iCompass and to utilize MergeLive to help with the transition. See update under item I.B.(1)(c) Staff have completed training the Diligent Communities system and City Council will be transitioning to online packets in May. City Council has fully transitioned to online packets and live streaming on YouTube. MergeLive continues to provide AV support for City Council meetings to assist in navigating the live streaming component of the Diligent system.
|  | 2. | Provide for environmental protection through appropriate programs and regulation | a. | Update FOG (Fats, oils and grease) program | DPW | On September 18, City Council adopted FOG Ordinance (Chapter 86 Utilities, Article VI, Installation and maintenance of grease interceptors; Discharge prohibitions). Restaurants have received information about the program in writing and in person. The ordinance will go into effect January 1, with the grease dumpsters remaining in place until March 1 to give time for restaurants to make the transition. Staff is meeting with restaurants who need further guidance and direction. Restaurants still in transition of the new Ordinance. Restaurants have signed contracts with vendors to install self contained FOG items on site, however, material and labor shortages have caused delays in installation. Many restaurants are still awaiting installation scheduling.
|  |  |  | b. | Evaluate programs for commercial refuse management including dumpster locks, cameras, etc. | DPW | The Police and Public Works departments have reviewed camera options and will be recommending additional camera installations to Council. Cameras were approved by City Council for installation near Mary Alexander dumpster location and continuing to work on developing a plan for additional locations. Still awaiting installation of cameras on Mary Alexander Ct. dumpster. Installation is scheduled for July. Cameras have been installed on the Mary Alexander Ct. dumpster and other locations for cameras are under evaulation.
|  |  |  | c. | Upgrade DPW fuel pump | DPW | An RFP has been developed and is under review. A contract was awarded to Oscar Larsen to complete the upgrade, which includes fuel management software. The materials and parts have been ordered and will be installed once received. We are also evaluating the option to add fleet management software to the fuel management software. The fuel management system has been installed and GPS software has been installed on all the vehicles. COMPLETE
C. | Contemporary and responsive regulation | 1. | Ensure ordinances comply with legal standards and reflect present conditions | a. | Update City Ordinances related to City Parks | CM | No update. Staff met with Northville Township staff to review the Shared Services Agreement related to parks and recreation. This work is on hold due to the planning staff transition. Current focus is on the Tree Ordinance, the Green Ordinance Audit, an update to the Property Maintenance Code, and a potential air condenser and emergency generator ordinance. Updates to the Park Ordinance will be addressed as staff is able. No additional update this quarter
|  |  |  | b. | Review Tree Ordinance | CM | No update. Staff Consultant is currently drafting language and will work on providing an update this Spring/Summer. A draft ordinance has been developed and is under internal review. Draft ordinance revisions will be presented to the Planning Commission for discussion and potential action in July. COMPLETED. New ordinance adopted by City Council on September 5, 2024.
|  |  |  | c. | Review lot coverage and non-permeable surface requirements to manage stormwater and runoff | CM | No update. A Request for Proposals has been released to conduct a Green Ordinance Audit to examine the City's codes, policies and operational procedures to determine where barriers exist to protecting water resources and the use of Low Impact Development practices. A contract has been awarded to Birchline Planning LLC to complete the Green Ordinance Audit. Birchline Planning has completed stakeholder interviews and is working on the ordinance review. A preliminary analysis and recommendations are expected to be available for City Council and the Planning Commission in August. Birchline Planning has submitted its preliminary recommendations on the Green Ordinance Audit. The initial findings were provided to staff, the Sustainability Team, and the Planning Commission. Staff is working with these groups to evaluate what elements of the recommendations can be feasibly implemented, as well as the best path forward for the project.
V. | Enhanced Public Assets: Transportation and Infrastructure
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Integrated mobility network | 1. | Provide for safe multiple modes of transportation throughout the City | a. | Complete non-motorized transportation plan and develop implementation recommendations | CM/DPW | The Non-Motorized Transportation Plan has been completed including review by the Mobility Network Team and online public input. The final plan will be presented to Council in October for possible adoption. City Council adopted the 2023 Northville Non-Motorized Transportation Plan at the October 2, 2023 meeting. COMPLETED
|  |  |  | b. | Complete traffic calming report and adopt traffic calming toolkit for application in future projects | CM/DPW | The Traffic Calming Report has been completed. The traffic calming report and tool kit will be presented to City Council on February 5 with a recommendation to adopt. Finalizing process and documents prior to implementing. Support documents for the program are nearing completion for implementation and posting on the web page. Documents are completed and will be posted in October.
B. | Stable transportation infrastructure | 1. | Provide safe roads | a. | Review and update street asset management plan | DPW | Reviewing Proposal. The City Engineering firm will begin this project in early 2024 OHM will be starting the asset management plan review in April 2024 Plan review is underway. Plan review is underway. OHM is focusing on developing estimated costs and a preliminary CIP
|  |  |  | b. | Evaluate Cady Street re-routing proposal | DPW | City staff continue to communicate with Wayne Co. regarding this concept. No update. No Update No Update This project is not being pursued at this time.
|  |  |  | c. | Repair High Street culvert | DPW | No Update - Grant status Nov. 2023. The City did not receive the funding requested for this project so staff, with the support of OHM, will continue researching funding options. Staff and OHM continue to research potential funding options for this project. A request was submitted to Congresswoman Dingle for 2025 Community Project Funds for this project. The city has been awarded $750,000 in funding for this project and will be completing the grant acceptance process in upcoming months.
|  |  |  | d. | Construct round-about at 7 Mile /Center | DPW | An engineering consultant services contract has been awarded for project preliminary design and development of an estimate of probable cost. Preliminary engineering design has been completed and will be presented to City Council for input on February 5, 2024. 60% Design complete, working with Wayne County with final design. Working on finalizing landscaping concept. Plans are 80% and an update will be presented to City Council in July. A public information meeting was held on August 12 to share information about the roundabout at Center Street and 7-mile.
C. | Reliable public services | 1. | Continue investments in neighborhood streets, water and sewer improvements | a. | Conduct a water and sewer rate study | DPW/FIN | RFP in review. City Council awarded a contract to Municipal Analytics in November. The study is complete and will be presented to City Council on April 8, 2024. Rates have been incorporated into approved budget with an effective date of June 1, 2024. COMPLETE
|  |  |  | b. | Implement water reservoir removal | DPW | Pending Water and Sewer Rate Study. Pending water and sewer rate study and DWRF. Pending water and sewer rate study and DWFR. Requests were submitted to Senators Stabenow and Peters for a FY25 Appropriation for this project. The city has been awarded $1 million in funding for this project. Construction plans are 70% complete. Once finished, plans will be submitted to Great Lakes Water autority and EGLE for approval and permitting.
|  |  |  | c. | Establish sanitary sewer capacity and procedure with Oakland in key areas | DPW | Developing a MOU to make the connection to Oakland Co. sewers and establish the sewer as a Chapter 21 Drain. A new sewer connection to the Oakland County system has been engineered and is currently under review by Oakland County. Oakland County is working with Wayne County. to establish this portion of the system as an intercounty drain. The necessary agreements will be forwarded to Council once complete The Chapter 21 Drain petition and resolution on April 1 that is necessary to allow a the new sewer connection was approved by Council The approved drain petition and resolution has been submitted to the state of Michigan for review. The petion and resolution are still under review, which can take several years.
D. | Quality public facilities | 1. | Preserve existing public facilities | a. | Assess and recommend changes to the elevators and HVAC systems at Allen Terrace | AT | Implemented new elevator service contract. Both elevators have been serviced and are running. Still waiting on boiler information. The boiler replacement has been postponed due to staff receiving HVAC training and being able to maintain the existing system while we assess funding options. AT decided to replace the boilers this year due to the low purchase price and installation costs. AT is currently pricing elevator replacement as well. Elevator 1 has needed many repairs. Instead of continually funding repairs we find it was better to purchase the new ones earlier. Boilers have been delivered and will be installed in July or August. Elevators have been ordered and are expected late fall. Boiler installation is complete and functioning. The elevator renovations are anticipated to be completed in November or December.
|  |  |  | b. | Assess the City Hall/Fire Station roof for repair or replacement | CM/DPW | The 2018 Assessment was updated and construction plans are under design. A roofing consultant contract was awarded at the September 18 meeting. Preliminary plans have been developed and bids are expected to be let in late January. A contract has been awarded to KJP Roofing to replace the roof. The work is tentatively schedule for May, 2024. The roof is scheduled to be replaced in July. The project also includes gutter replacement and repair of an improper roof installation above the Police canopy. The City Hall roofing project is 90% complete. All that remains are some minor issues to be addressed before the contract is closed.
|  |  |  | c. | Update activity rooms in Allen Terrace (exercise room, library, game room, computer room) | AT | Purchased new monitors for computer room and exploring options for NEW exercise equipment. A CDBG application has been developed for funds to install new flooring in the activity rooms. Mayor is pursuing a donation of exercise equipment for us from Planet Fitness. Exercise room has been updated with new paint and flooring waiting for the equipment. AT is expecting new equipment the end of June. AT received 3 items from Planet Fitness for the Fitness area. Updated computers ( Old City Hall computers) in the computer lab , as well as a new printer.
|  | 2. | Ensure efficient use of existing facilities | a. | Complete the 1st floor office renovation at City Hall. | CM | Construction plans are completed and bids have been received. A contractor recommendation will be forwarded to City Council for consideration in October. The office renovation is approximately 75% completed. The contractor is awaiting delivery of the cabinetry for the kitchenette and the doors for the various offices. Staff has met with M. Architects to discuss a police locker room renovation and the Fire Department space needs. The office renovation has been completed and staff are moved in. COMPLETED
VI. | Enhanced Public Assets: Recreational and Cultural Opportunities
| Intended Outcome |  | Strategy |  | Action | Depts | Progress Notes
A. | Contemporary recreational facilities | 1. | Ensure visitors of all abilities can access recreation programs and facilities | a. | Complete Ford Field gateway and bank stabilization project | CM | Three design concepts have been developed and meetings are being held with stakeholders to review and provide input. A final gateway design has been developed and was reviewed by City Council on December 18. A consultant services contract was awarded to OHM to develop bid documents for the project. The final construction scope is defined and EGLE permit applications submitted. Bidding is expected to take place in May. The EGLE permit has been received. Construction plans are 80% complete. Costs were received from DTE to bury the overhead power lines and OHM is coordinating discussions with joint users to bury their lines. Construction is anticipated for spring, after the Serenity Point project is complete. OHM is working with DTE to coordinate the Gateway construction plans with the utility pole replacement project. The design is being finalized for the retaining wall around Robert's Rock and we are working toward project bidding by the end of the year, for spring construction.
|  |  |  | b. | Develop a playground improvement plan for Fort Griswold that is accessible and reflects community expectations | CM | No update at this time. A landscape design firm, Landscape Architects and Planners, has begun to develop a design plan for the playground which will be used to pursue additional funding. Playground Steering Committee has been formed to guide the public input process and assist in identifying funding opportunities. A community input meeting was held on June 27 to gather ideas for replacing the playground. The information collected will be used to develop a Request for Proposals from playground equipment suppliers for designs for further review and discussion. Fundraising materials are being developed for a November launch.
|  | 2. | Enhance visitor recreational experiences through infrastructure improvements | a. | Identify alternative location for Farmers Market | CM/DPW | Discussions are ongoing to identify a temporary location for the market for next season. The City and the Chamber are working toward finalizing a temporary location for the market. A temporary location for the 2024 Market has been secured at the Highland Lakes Shopping Center. Conversations continue around identifying a permanent location for the market. The city and Township have partnered to identify a permanent location for the market and pursue a property acquisition. The city and township are in a due-diligence period regarding the purchase of the property.
|  |  |  | b. | Finalize a design for improvements to Serenity Point | CM | No update at this time. The grant has been transferred to the Randolph Street intercounty drain drainage board for implementation by Oakland County who have contracted with HRC to develop construction plans for the project. Construction plans are being developed and it is expected that the project will be bid this spring and constructed this summer/fall. This project is being coordinated with the Gateway project because there will be some overlap in both timing and location of both projects. Construction plans are complete and the project is proposed to be let for bids in July, with construction is August and September. The Oakland County Water Resource Commissioner opened bids for the project and selected VIL Construction for the work. A contract will be awarded as soon as approval is received from the granting agency and work is expected to being in January.
|  |  |  | c. | Develop a plan to fund and construct restrooms at Ford Field Park | CM | No update at this time. Funding options for the restrooms at Ford Field Park West will be incorporated into the grant program outlined in Action a, of Strategy 2 above. A Land and Water Conservation Fund grant application has been submitted for funds to construct the restroom and accessible walkways. The city will learn in December if the request was successful. Preliminary grant scores are expected in August and the city will have the opportunity to adjust the grant application to increase points. Preliminary scores were received in September and we are not currently within the fundable range. Out of 380 possible points, 50 are based on economic need of the community so it is challenging to make those points up in other areas of the scoring criteria. However we were able to submit additional information based on the reviewer's feedback and are hopeful that this will raise our scores into the fundable range.
B. | Responsive and responsible planning | 1. | Develop long-range plans to guide future improvements that are reflective of the community | a. | Develop a Northville Riverwalk Plan | CM | No update at this time. Plans for a riverwalk are being discussed as part of the grant program outlined in Action a, of Strategy 2 above. Funding discussions are ongoing with the Ralph Wilson Foundation, DTE and other potential partners. Planning is ongoing. Staff has met with the owner of the Foundry Flask property to discuss options for trail routes across the property and is working with DTE to accommodate a trail across the DTE substation at the corner of Griswold and Beal Street. Discussions have been held with staff from the Ralph Wilson Foundation, the DTE Foundation and SEMCOG to discuss granting options.
|  |  |  | b. | Partner with Northville Township to update the 5-year Parks and Rec. Plan | CM | The community survey is underway. A draft plan has been developed and released for public review. The 2024 Park and Recreation Plan was completed, submitted to the MDNR, and approved. It will be valid until December, 2028. COMPLETED
|  |  |  | c. | Finalize a design for the River Daylighting project | CM | The River Restoration Task force has negotiated a recommended park plan with HP and this plan is included in the Site Plan that has been submitted for review and approval. The final park site plan was approved by the Planning Commission as part of the site plan packet. Staff continues to work with HP to develop the design details. Community members have launched a fundraising campaign to relocate and renovate the log cabin that will be displaced during site demolition. City staff continue to work with HP on the River Park: - 3 consultant services contracts have been awarded for park design, 1 is pending - the demolition contract has been awarded - large portion of the funds needed for the log cabin have been raised - preliminary landscape and grading plans for River Park have been provided to staff for review - lighting and infrastructure plans for Central Park have been provided to staff for review Demolition of the buildings on the park site are complete and soil tests to determine the type and extent of any contamination have been completed in three of the five quadrants identified for testing. Bids have been secured for park construction and it is anticipated that a contract recommendation will be forwarded to City Council in August. City Council awarded a construction contract to BNV on August 19 and construction began in September. The river bid has been excavated and all contaminated soil removed from site. BNV will continue with the final grading and will be installing the boulders, riffles and other structures in October.